## Sheet1
= Planning
|  |  |  | = Actual | FEBRUARI | [25 empty] | MARET | [30 empty] | APRIL | [29 empty] | MEI | [30 empty] | JUNI | [29 empty] | JULI | [30 empty] | AGUSTUS
[5 empty] | Week 1 | [7 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 |  |  |  | Week 1 |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [7 empty] | Week 1 | [5 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 |  |  | Week 1 |  |  |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [5 empty] | Week 1 | [7 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [7 empty] | Week 1 | [5 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 |  |  |  | Week 1 |  |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
Deskripsi Pekerjaan |  |  | PIC | Progress | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Penetapan Spesifikasi
| Template Admin |  | Abdul | 0% | bar: Week 1 10 to Week 2 17
| Template Artikel |  | Abdul | 0% | bar: Week 1 10 to Week 2 17
| Video Opening |  | Wildan | 0% | bar: Week 1 10 to Week 2 17
| Video Ending |  | Wildan | 0% | bar: Week 1 10 to Week 2 17
| Video Editor |  | Wildan | 0% | bar: Week 1 10 to Week 2 17
| Merancang ERD |  | Dedi | 100% | bar: Week 1 6 to Week 2 17
Design System
| Design Database |  |  | 0% | bar: Week 2 17 to Week 1 2
| Design Antarmuka |  |  | 0% | bar: Week 2 17 to Week 2 9
Pengujian Rancangan
Fitur X (Data Di Sesuaikan)
Fitur X (Data Di Sesuaikan)
| Pengujian Rancangan |  |  | 0% | bar: Week 1 1 to Week 2 9
Implementasi System
Pembuatan Program
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 3 10 to Week 3 16
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 3 10 to Week 3 16
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 4 17 to Week 4 23
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 4 17 to Week 4 23
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 5 24 to Week 5 31
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 5 24 to Week 5 31
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 1 1 to Week 1 6
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 1 1 to Week 1 6
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 2 7 to Week 2 13
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 2 7 to Week 2 13
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 3 14 to Week 3 20
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 3 14 to Week 3 20
|  | Form X (Data disesuaikan) |  | 0% | bar: Week 4 21 to Week 4 27
| Pengujian Program |  |  | 0% | bar: Week 4 21 to Week 1 4
| Hosting and Domain |  |  | 0% | bar: Week 2 5 to Week 3 17
Integrasi System
| Penerapan |  |  | 0%
| Pengujian |  |  | 0%
Final
| Live |  |  | 0%